## Sheet1
Team Members:
Prasad Shende | pushende@ncsu.edu
Shivani Mehendarge | ssmehend@ncsu.edu
Poovanna | pkpoonap@ncsu.edu
Text Classification:
Topic: Classify ireviews on IMDB Dataset | https://ai.stanford.edu/~amaas/data/sentiment/
Tasks: | Sub-tasks: | Responsibility | Timeline | Status
Literature Survey: | Read About Sentiment Analysis | All | 8th March | Done
| Survey about requirements | All | 8th March | Done
| Paper survey on word embeddings | All | 15th March | Done
| GloVe | All | 15th March | Done
| CNN | All | 15th March | Done
| RNN | All | 15th March | Done
| HAN | All | 15th March | Done
Prepare Kernels | CNN without word embeddings/with basic vector representation | Prasad | 23rd March | Done
| RNN without word embeddings/with basic vector representation | Poovanna | 23rd March | Done
| HAN without word embeddings/with basic vector representation | Shivani | 23rd March | Done
| GloVe + CNN | Prasad | 3rd April | Done
| GloVe + RNN | Shivani | 3rd April | Done
| GloVe + HAN | Poovanna | 3rd April | Done
Optimize | GloVe + CNN | Prasad | 14th April | Done
| GloVe + RNN | Shivani | 14th April | Done
| GloVe + HAN | Poovanna | 14th April | Done
Conclude Results | Use CV/ other techniques | All | 22nd April | Done
| Create Video | Poovanna, Shivani | 25th April | Done
| Create PPT | Prasad | 26th April | Done
| Compare different nn archs | All | 29th April | Done
| Create Report | All | 30th April | Done